## Sheet1
Tasks | Time Allocation (person days) | Planned Start | Planned End | Optimistic Time Estimates (person days) | Most Likely Time Estimates (person days) | Pessimistic Time Estimates (person days) | Estimated Time Te= (T0 + 4Tm + Tp)/ 6
Requirement Analysis and Project Planning | 10 | 2002-01-01 | 01/14/2002 | 7 | 10 | 13 | 10
Setting up the Environment | 6 | 2002-01-01 | 2002-08-01 | 3 | 6 | 9 | 6
Software Construction | 80 | 01/15/2002 | 05/15/2002 | 48 | 83 | 100 | 80
Unit Testing | 30 | 05/16/2002 | 06/28/2002 | 20 | 28 | 33 | 27.5
User Training | 5 | 07/22/2002 | 07/26/2002 | 4 | 5 | 6 | 5
System Testing | 15 | 2002-01-07 | 07/19/2002 | 10 | 15 | 20 | 15
User Documentation | 30 | 01/15/2002 | 02/28/2002 | 23 | 28 | 45 | 30
Data Migration | 20 | 01/15/2002 | 02/15/2002 | 18 | 18 | 30 | 20
Conduction User Acceptance test | 20 | 2002-01-08 | 08/31/2002 | 14 | 21 | 22 | 20