## Slide 1: VII.3 SOFTWARE PROJECT MANAGEMENT

## Slide 2: FUNCTION POINT METRICS
Function-oriented software metrics use a measure of the functionality delivered by the application as a normalization value. Function point measures functionality from the user’s point of view, that is, on the basis of what the user requests and receives in return form the system. Since ‘functionality’ cannot be measured directly, it must be derived indirectly using other direct measures.
Function points are derived using an empirical relationship based on countable measures of software’s information domain and assessments of software complexity.

## Slide 3: Contd..
Functions points are computed by completing the five information domain characteristics are determined and counts are provided in the appropriate table location. Information domain values are defined in the following manner:
    Number of user inputs
    Number of user outputs
    Number of user inquiries
    Number of files
    Number of external interfaces
To compute function points (FP), the following relationship is used:
FP=count total x [0.65+0.01 x ∑ (Fi)]

## Slide 4: COMPUTING FUNTION POINTS TABLE
Weighting factor
Measurement parameter Count Simple
Number of user inputs 32 x 3 = 96
Number of user outputs 16 x 4 = 64
Number of user inquiries 9 x 3 =27
Number of files 8 x 7 =56
Number of external interfaces 2 x 5 =10
Count total-------------------------------------------253

## Slide 5: The Fi (i=1 to 14) are “complexity adjustment values” based on responses to the following questions:
Does the system require reliable backup and recovery? 3
Are data communications required? 3
Are there distributed processing functions? 0
Is performance critical? 2
Will the system run in an existing, heavily utilized operational environment? 3
Does the system require on-line data entry? 3
Does the on-line data entry require the input transaction to be built over multiple screens or operations? 0

## Slide 6: Contd..
Are the master files updated on-line? 3
Are the inputs, outputs, files, or inquiries complex? 0
Is the internal processing complex? 0
Is the code designed to be reusable? 4
Are conversion and installation included in the design? 0
Is the system designed for multiple installations in different organizations? 2
Is the application designed to facilitate change and ease of use by the user? 4

## Slide 7: Contd..
∑(Fi) = (3+3+0+2+3+3+0+3+0+0+4+0+2+4)
= 27
By substituting those values we get function points (FP),
FP = count total x [0.65+0.01 x ∑ (Fi)]
= 253 x [0.65+0.01 x 27]
= 253 x [0.65+0.27]
=232.76

## Slide 8: COCOMO MODEL
COCOMO introduced a hierarchy of software estimation models for Constructive Cost Model.
The original COCOMO model become one of the most widely used and discussed software cost estimation models in the industry. It has evolved into a more comprehensive estimation model, called COCOMO II. Like its predecessor, COCOMO II is actually a hierarchy of estimation models that address the following areas:-

## Slide 9: Contd..
  Application composition model
  Early design stage model
  Post-architecture-stage model
COCOMO II models require sizing information. Three different sizing options are available as part of the model hierarchy:-
  object points,
  Function points, and
  lines of source code.

## Slide 10: COMPLEXITY WEIGHTING TABLE
OBJECT TYPE COMPLEXITY NUMBER OF INSTANCES
WEIGHT: SIMPLE
Screens 1 X 9 = 9
Reports 2 X 3 = 6
Objects point total = 15
When component-based development or general software reuse is to applied, the per cent of reuse is estimated and the object point count is adjusted:
NOP = (Object points) x [(100-%reuse)/100] [NOP = new object points]
= 15 x [(100-0)/100] [%reuse = 0]
= 15 x 1
=15
To derive an estimate of effort based on the computed NOP value, a “productivity rate” must be derived.

## Slide 11: CONTD..

## Slide 12: PRODUCTIVITY RATES TABLE
Developer’s experience/capability Nominal
Environment maturity/capability
Nominal
PROD 13

## Slide 13: Estimated effort
Productivity rate for different levels of developer experience and development environment maturity. Once the productivity rate has been determined, an estimate of project effort can be derived as
Estimated effort = NOP/PROD
= 15/13
=1.15 person-month
Therefore, Estimated Effort is 1.15 person-month