## Basic Gantt Chart
[7 empty] | REQUIREMENTS ANALYST | [13 empty] | DESIGNER | [13 empty] | DEVELOPER | [20 empty] | TESTER | [13 empty] | MANAGER
TASK ID | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
[7 empty] | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
1 | Project Initiation and Survey
1.1 | Initial Research & Starting the Report | Amit Katyal | 2021-06-08 | 2021-07-08 | 2 | 100% | bar: WEEK 1 F to WEEK 1 S
1.2 | Describing the Problem & Objectives | Amit Katyal | 2021-07-08 | 2021-10-08 | 4 | 100% | bar: WEEK 1 S to WEEK 1 T
1.3 | Proposing the Timeline | Amit Katyal | 2021-11-08 | 14/8/2021 | 4 | 100% | bar: WEEK 1 W to WEEK 2 S
1.4 | Survey Creation | Amit Katyal | 2021-12-08 | 13/8/2021 | 2 | 100% | bar: WEEK 1 T to WEEK 2 F
1.5 | Collecting Responses | Amit Katyal | 13/8/2021 | 18/8/2021 | 6 | 100% | bar: WEEK 2 F to WEEK 2 W
1.6 | Concluding the Survey | Amit Katyal | 18/8/2021 | 19/8/2021 | 2 | 100% | bar: WEEK 2 W to WEEK 2 T
2 | Designing Phase
2.1 | Data Flow & Architectural Diagram | Shubham Chauhan | 20/8/2021 | 22/8/2021 | 3 | 100% | bar: WEEK 3 F to WEEK 3 S
2.2 | Functional & Design Requirements | Shubham Chauhan | 22/8/2021 | 26/8/2021 | 5 | 100% | bar: WEEK 3 S to WEEK 3 T
2.3 | Wireframing | Shubham Chauhan | 26/8/2021 | 29/8/2021 | 4 | 100% | bar: WEEK 3 T to WEEK 4 S
2.4 | Class Responsibility Collaboration | Shubham Chauhan | 29/8/2021 | 30/8/2021 | 2 | 100% | bar: WEEK 4 S to WEEK 4 M
2.5 | Prototyping | Shubham Chauhan | 30/8/2021 | 2021-02-09 | 4 | 100% | bar: WEEK 4 M to WEEK 4 T
3 | Development Phase
3.1 | Authentication | Tushar Sethi | 2021-03-09 | 2021-06-09 | 4 | 100% | bar: WEEK 5 F to WEEK 5 M
3.2 | Chat Functionality | Tushar Sethi | 2021-07-09 | 2021-11-09 | 5 | 100% | bar: WEEK 5 T to WEEK 6 S
3.3 | Contact Feature | Tushar Sethi | 2021-09-09 | 2021-11-09 | 3 | 100% | bar: WEEK 5 T to WEEK 6 S
3.4 | Events | Tushar Sethi | 2021-11-09 | 13/9/2021 | 3 | 100% | bar: WEEK 6 S to WEEK 6 M
3.5 | Course Management | Tushar Sethi | 14/9/2021 | 15/9/2021 | 2 | 100% | bar: WEEK 6 T to WEEK 6 W
3.6 | Teachers Management | Tushar Sethi | 16/9/2021 | 17/9/2021 | 2 | 100% | bar: WEEK 6 T to WEEK 7 F
3.7 | Students Management | Tushar Sethi | 17/9/2021 | 18/9/2021 | 2 | 100% | bar: WEEK 7 F to WEEK 7 S
3.8 | Timetable Management | Tushar Sethi | 18/9/2021 | 18/9/2021 | 1 | 100% | bar: WEEK 7 S
3.9 | Document Feature | Tushar Sethi | 19/9/2021 | 20/9/2021 | 2 | 100% | bar: WEEK 7 S to WEEK 7 M
3.10 | Notification Feature | Tushar Sethi | 19/9/2021 | 21/9/2021 | 3 | 100% | bar: WEEK 7 S to WEEK 7 T
3.11 | Room Feature | Tushar Sethi | 21/9/2021 | 23/9/2021 | 3 | 100% | bar: WEEK 7 T to WEEK 7 T
3.12 | Canteen Management | Tushar Sethi | 22/9/2021 | 24/9/2021 | 3 | 100% | bar: WEEK 7 W to WEEK 8 F
3.13 | Initial Testing - Bug Fixes | Tushar Sethi | 23/9/2021 | 30/9/2021 | 8 | 100% | bar: WEEK 7 T to WEEK 8 T
4 | Testing Phase
4.1 | Initial Testing & Checks | Sachin Rathore | 23/9/2021 | 29/9/2021 | 7 | 100% | bar: WEEK 7 T to WEEK 8 W
4.2 | Making Bug Report | Sachin Rathore | 29/9/2021 | 30/9/2021 | 2 | 100% | bar: WEEK 8 W to WEEK 8 T
4.3 | Unit Testing | Sachin Rathore | 2021-01-10 | 2021-03-10 | 3 | 100% | bar: WEEK 9 F to WEEK 9 S
4.4 | Effort and Cost Tracking | Sachin Rathore | 2021-04-10 | 2021-06-10 | 3 | 100% | bar: WEEK 9 M to WEEK 9 W
4.5 | Cyclomatic Complexity | Sachin Rathore | 2021-06-10 | 2021-06-10 | 1 | 100% | bar: WEEK 9 W
4.6 | Performance Testing | Sachin Rathore | 2021-06-10 | 2021-07-10 | 2 | 100% | bar: WEEK 9 W to WEEK 9 T
5 | Compilation Phase
5.1 | Monitor Progress | Ashutosh Jha | 2021-08-10 | 2021-10-10 | 3 | 100% | bar: WEEK 10 F to WEEK 10 S
5.2 | Evaluating Project Performance | Ashutosh Jha | 2021-09-10 | 2021-11-10 | 3 | 100% | bar: WEEK 10 S to WEEK 10 M
5.3 | Finalise Report | Ashutosh Jha | 2021-10-10 | 2021-12-10 | 3 | 100% | bar: WEEK 10 S to WEEK 10 T
5.4 | Project Performance | Ashutosh Jha | 2021-12-10 | 13/10/2021 | 2 | 100% | bar: WEEK 10 T to WEEK 10 W
5.5 | Final Project Revision | Ashutosh Jha | 14/10/2021 | 14/10/2021 | 1 | 100% | bar: WEEK 10 T